## BlockChain In IOT
Task Name | Duration | Start | Finish | Predecessors | Assigned To | % Complete | Status | Comments
Planning Phase | 7d | 2020-11-24 | 2020-12-02 |  | Team |  | Completed
Scrum Meeting Plan
Project Selection
Sprint Planning
1st Sprint Review | 14d | 2020-12-02 | 2020-12-21
Requirements Gathering | 3d | 2020-12-02 | 2020-12-04 |  | Team | 95 | Completed
Architecture | 2d | 2020-12-06 | 2020-12-07 |  | Parag, Safir | 95 | Completed
Network Setup | 4d | 2020-12-09 | 2020-12-14 |  | Vidya | 40 | In Progress
Smart Contract Logic Scenarios | 3d | 2020-12-16 | 2020-12-18 |  | Team | 95 | Completed
Requirements and Design Review | 2d | 2020-12-20 | 2020-12-21 |  | Team | 95 | Completed
2nd Sprint Review | 15d | 2020-12-23 | 2021-01-12
Requirement analysis | 1d | 2020-12-23 | 2020-12-23 |  | Team | 95 | Completed
Network Setup | 1d | 2020-12-24 | 2020-12-24 |  | Vidya, Safir | 95 | Completed
Codechain Setup and Smart Contract | 4d | 2021-01-05 | 2021-01-08 |  | Safir | 70 | In Progress
Unit testing | 2d | 2021-01-08 | 2021-01-11 |  | Team | 95 | Completed
3rd Sprint Review | 20d | 2021-01-13 | 2021-02-09
Requirement analysis | 5d | 01-13-21 | 2021-01-18 |  | Team | 95 | Completed
Modification of Smart Contracts | 5d | 01-18-21 | 01-26-21 |  | Safir | 95 | Completed
Network Re-Organisation | 5d | 01-18-21 | 01-26-21 |  | Vidya | 90 | Completed
Implementation Client Application | 6d | 2021-01-27 | 2021-02-03 |  | Safir, Pranay, Parag | 95 | Completed
Testing | 3d | 2021-02-04 | 2021-02-08 |  | Team | 95 | Completed
Final Review | 2d | 2021-02-07 | 2021-02-08 |  | Team
Documentation | 26d | 2021-02-10 | 2021-03-17 |  | Team | 100 | Completed
Final Presentation | 10d | 2021-03-18 | 2021-03-31 |  | Team | 100 | Completed